## Sheet1
SPRINT 1

Story 0	ph
Setup repository folder structure	1
Decide database structure (tables and relations)	2
Create database	1
Study/Decide general GUI design (mockup for the whole project)	2
Study/Decide front-end framework	1
Study unit testing in web applications	2
Study integration testing in web applications	2

Story 1
Design GUI for login	1
Send credentials to server	1
Connect to database	1
Query database for checking credentials	1
Redirect to update password form if first access	1
Update password if first access	1
Retrieve marks from database	1
Visualize marks	1
Apply filters (order, group by subject…)	2
Unit test	2
Integration test	2
Code review	1.5
Write use case	0.5

Story 2
Design GUI to insert lecture topics	1
Check time constraints	1.5
Send form data to server	1
Update database	1
Unit test	2
Integration test	2
Code review	1.5
Write use case	0.5

Story 3
Design GUI to record parent	1
Send parent info to server	1
Add parent to database	1
Send parent credentials via email	2
Unit test	2
Integration test	2
Code review	1.5
Write use case	0.5

Story 4
Expand parent registration GUI to record student associated	1
Send student credentials to server	1
Add student to database	1
Associate student to parents	1
Unit test	2
Integration test	2
Code review	1.5
Write use case	0.5

Story 5
Design GUI to enter class composition	1
Retrieve list of students and class	1
Add search filter for students	2
Update database	1
Unit test	2
Integration test	2
Code review	1.5
Write use case	0.5

Story 6
Design GUI to insert grades	1
Send form data to server	1
Update database	1
Unit test	2
Integration test	2
Code review	1.5
Write use case	0.5

total ph:	78.5
# tasks:	59

SPRINT 2

Preparation of Sprint 2
Fix adaptive layout for header and dashboard	2
Fix adaptive layout for forms/main content	2	4
Add python script to run tests in windows	1.5
Fix 10/10L decimal mark insertion	0.5
Code refactoring (redirect functions, https)	1
Test refactoring (global variables, waitElement instead of wait)	2
Populate database with dummy entries	1.5
Put child selection in the dashboard	1.5
Enable use of same credentials for different roles / (user type selection in header)	2
Export functions in utility.php	1.5
Update test with exported functions	2
Study docker	2
Setup docker for project	1.5
Add search box in class composition form	1.5
Visual testing	6
Study html/css/bootstrap	6

Story 7
Design GUI for assignment visualization	1
Retrieve list of assignments for specific student	1
Visualize assignments	2
Apply filters	2
Unit test	1.5
Integration test	1.5
Code review	1

Story 30
Design GUI for setup of accounts	1
Show form to insert new account	1
Insert new credentials in database	1
Add home page for principal	1
Unit test	1.5
Integration test	1.5
Code review	1

Story 8
Design GUI for attendances	1
Retrieve attendances for specific student	1
Visualize attendance	1
Unit test	1.5
Integration test	1.5
Code review	1

Story 9
Design GUI for absence record	1
Show form to insert absences	1
Insert absences in database	1
Unit test	1.5
Integration test	1.5
Update story 6 with presence check	1
Code review	1

Story 10
Design GUI for late entrances	1
Show form to insert entrances	1
Insert entrances in database	1
Unit test	1.5
Integration test	1.5
Update story 6 with presence check	1
Code review	1

total ph:	75.5
# tasks:	50

SPRINT 3

Preparation of Sprint 3
Update database	2
Fix story 7	2
Add file visualization in story 7	1.5
Create dockerfile	3
Fix story 30: disable edit if existing SSN	1
Fix past tests	4
Change user-type menu layout	1

Story 11
Design GUI for assignment recording	1.5
Show assignment already uploaded	1.5
Enable file uploading	1.5
Update database	1
Update story 7	1.5
Unit test	1.5
Integration test	1.5
Code review	1

Story 12
Design GUI for official communications	1.5
Update database	1.5
Unit test	1.5
Integration test	1.5
Code review	1

Story 13
Design GUI for early leaving	1
Update database	1
Update story 10	1.5
Unit test	1.5
Integration test	1.5
Code review	1

Story 14
Design GUI to publish timetable	1
Update database	1
Update story 10	1.5
Unit test	1.5
Integration test	1.5
Code review	1

Story 15
Design GUI to publish support material	1.5
Upload file in server	1.5
Unit test	1.5
Integration test	1.5
Code review	1

total ph:	64.5
# tasks:	42