## Sheet1
Story 0	ph		total ph:
Setup repository folder structure	1		78.5
Decide database structure (tables and relations)	2
Create database	1		# tasks:
Study/Decide general GUI design (mockup for the whole project)	2		59
Study/Decide front-end framework	1
Study unit testing in web applications	2
Study integration testing in web applications	2

Story 1
Design GUI for login	1
Send credentials to server	1
Connect to database	1
Query database for checking credentials	1
Redirect to update password form if first access	1
Update password if first access	1
Retrieve marks from database	1
Visualize marks	1
Apply filters (order, group by subject…)	2
Unit test	2
Integration test	2
Code review	1.5
Write use case	0.5

Story 2
Design GUI to insert lecture topics	1
Check time constraints	1.5
Send form data to server	1
Update database	1
Unit test	2
Integration test	2
Code review	1.5
Write use case	0.5

Story 3
Design GUI to record parent	1
Send parent info to server	1
Add parent to database	1
Send parent credentials via email	2
Unit test	2
Integration test	2
Code review	1.5
Write use case	0.5

Story 4
Expand parent registration GUI to record student associated	1
Send student credentials to server	1
Add student to database	1
Associate student to parents	1
Unit test	2
Integration test	2
Code review	1.5
Write use case	0.5

Story 5
Design GUI to enter class composition	1
Retrieve list of students and class	1
Add search filter for students	2
Update database	1
Unit test	2
Integration test	2
Code review	1.5
Write use case	0.5

Story 6
Design GUI to insert grades	1
Send form data to server	1
Update database	1
Unit test	2
Integration test	2
Code review	1.5
Write use case	0.5